## Project Schedule & Gantt Chart
No | Task Name | Assigned members | 2026-04-01 |  |  |  |  | 2026-05-01 |  |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-01
|  |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2
| Brainstorming | all Members of the team | bar: 2026-04-01 W1 to 2026-04-01 W2
| Sketches / 3D model | Rafael | bar: 2026-04-01 W3 to 2026-04-01 W4
| Gantt chart | all Members of the team | bar: 2026-04-01 W5 to 2026-05-01 W1
M1 | Planning (05.05.2026) | bar: 2026-04-01 W1 to 2026-05-01 W1
| Base | Rostik & Amir | bar: 2026-04-01 W5 to 2026-05-01 W1
| Arm | Rostik & Amir | bar: 2026-05-01 W2 to 2026-05-01 W3
| Claw | Rostik & Rafael | bar: 2026-04-01 W5 to 2026-05-01 W3
| Integration | all Members of the team | bar: 2026-05-01 W4 to 2026-05-01 W5
M2 | Build (26.05.2026) | bar: 2026-04-01 W5 to 2026-05-01 W5
| Object detection | Amir | bar: 2026-05-01 W5 to 2026-06-01 W2
| Dimension measurements | Rafael | bar: 2026-05-01 W5 to 2026-06-01 W2
| Coordinates conversion algorithm | Rostik | bar: 2026-05-01 W5 to 2026-06-01 W2
| Integration | all Members of the team | bar: 2026-06-01 W3
M3 | Software (16.06.2026) | bar: 2026-05-01 W5 to 2026-06-01 W3
| Adjustments & Testing | all Members of the team | bar: 2026-06-01 W3 to 2026-06-01 W5
| Preparation for the final presentation | all Members of the team | bar: 2026-07-01 W1 to 2026-07-01 W2
M4 | Final Product (07.07.2026) | bar: 2026-06-01 W3 to 2026-07-01 W2

## Planning
Planning (Put your name if you are not available on those time slots)
Time | Monday | Tuesday | Wednesday | Thursday | Friday
2026-10-08 | Rafael | Rafael | Amir, Rafael | OFFIS | Amir, Rafael
2026-12-10 | Rafael | Embedded Lecture | Rostik, Rafael | OFFIS | Rafael
12-14 | Rafael | (Rostik) | Rostik, Rafael | Rostik | Amir, Rafael
14-16 | Rafael | OFFIS | Rafael | Rafael | ONLINE
16-18 |  | OFFIS
18-20 | Rostik |  | Rostik